## CARITAS KLA COVID-19 RESPONSE
CARITAS KAMPALA
CARITAS KAMPALA COVID-19 RESPONSE 2020 PROPOSED BUDGET
TIME FRAME FOR DISTRIBUTION OF ITEMES
[6 empty] | APRIL |  | MAY
| Activities | Qty | Unit cost | Freq | Amount UGX | 3rd Week | 4th Week | 1st Week | 2nd Week
OBJECTIVE 1: To prevent transmition of COVID-19 among the community by facilitating acess to hand washing facilities.
1.1 | Provide pedal-operated hand washing stations to community | 200 | 120000 | 1 | 24000000
1.2 | Provide Soap(5soap bars per station) | 1000 | 5000 | 1 | 5000000
1.3 | Provide Sanitizers to 1000 families | 1000 | 35000 | 1 | 35000000
| Sub-total |  |  |  | 64000000
2 | OBJECTIVE 2: To reduce hunger among 2000 vulnerable families in the community of Nsambya Gogonya 11 and Kamwanyi villages in Makidye Division Kampala District.
2.1 | Provide 10Kgs of Maize floor to 2000 families | 10 | 2500 | 2000 | 50000000
2.2 | Provide 5Kgs of beans to 2000 families | 5 | 3500 | 2000 | 35000000
2.3 | Provide 2 Kgs of Sugar to 2000 families | 2 | 5000 | 2000 | 20000000
2.4 | Provide 1Liter of cooking oil to 2000 families | 1 | 3000 | 2000 | 6000000
| Sub-total |  |  |  | 111000000
3 | OBJECTIVE 3: To Support health facilities and vulnerable communities with Personal Protection Equipment.
3.1 | Provide 20000 face masks to vulnerable heads of families | 20000 | 5000 | 1 | 100000000
3.2 | Provide PPE to St. Francis hospital and Mukwaya General Hospital
| Face Masks( N95) | 200 | 10000 | 1 | 2000000
| Gowns | 200 | 45000 | 1 | 9000000
| Gogles | 200 | 60000 | 1 | 12000000
| Gloves( pairs) | 200 | 13000 | 1 | 2600000
| Boots (pairs) | 200 | 25000 | 1 | 5000000
| Sub-total |  |  |  | 130600000
| Procurement costs | 5 | 100000 | 1 | 500000
| Transportation cost | 3 | 400000 | 1 | 1200000
| Communication costs | 6 | 50000 |  | 0
| Distribution costs( loading and offloading | 10 | 30000 | 3 | 900000
| Sub-total |  |  |  | 2600000
| Grand total |  |  |  | 308200000
|  |  | DOLLARS |  | 84438.3562
RATE 1DOLLAR: 3650UGX